## Sheet1
Edit Requested | Requested by | Date Received | Implemented (Y/N/D) | Comments
Change font size to make report easier to see | Rob O | 2014-04-09 | D | At this point, anything larger than a font 8 spreads the data out too far for the report. It will also make printing very difficult. Defered for now
Highlight the Area and Percentage overlap fields | Rob O | 2014-04-09 |  | Possibly highlight the field headings in a different color?
Have the report printable | Rob O, Jan C | 2014-04-09 |  | Wrap text in cells over a ceratain size to decrease width of report. Probably will only be able to print to landscape. Print to 8.5X11
Give user ability to save clipped data to permanent workspace | Rob O | 2014-04-09 | Y | Created new optional parameter to set workspace
Add regional office to header | Jan C | 2014-04-09 | Y | Summarized all District at the top of the report
Possibly group all the various Districts together: Forest, Municipalities, Regional Districts, Land, Land Title, Natural Resource Operations Admin Areas, Natural Resource Operations Operating Regions | Chris K | 2015-04-01 | Y | Created a nre Cataegory for 'Districts' and had these summarized at the top of the report.
Update Featureclass_Name to better describe/distinguish what Parks and Protected areas include (Provincial, ecological reserves) | Jan C | 2014-04-09 | Y | Updated Featureclass_Name to 'Provincial Parks, Protected Areas and Ecological Reserves'
Find out what Regional Parks are and update Featureclass_Name with a better descriptor | Jan C | 2014-04-09 | Y | Do some research on this shapefile to find the proper descriptor/explanation as to what these areas are
Some entries have blue section headings while others don’t. Not sure is this is on purpose or just missed, or? | Chris K | 2015-04-01 | D | This is indicated in the legend
Reserves can be grouped together: Mineral, Placer, Coal | Chris K | 2015-04-01 | Y | Prefaced each reserve with 'Reserve'
Tenure could probably be grouped together: Mineral, Placer, Coal | Chris K | 2015-04-01 | Y | Prefaced each reserve with 'Tenure'
There are other possible groupings. Not sure if you want those suggestions as well. | Chris K | 2015-04-01 | N | Waiting for recommendations
Regional Parks (& Municipal Parks?) – I didn’t believe that there is a layer for this except for an old layer that I think might have been created years ago and used internally. This could be misleading in that someone might think the data is current. Is it? | Chris K | 2015-04-01 | D | This layer is up-to-date and current.
Crown Granted 2 Post Mineral Claims - Is this a new mapping layer? I know Jack Leedham’s group was working on it. | Chris K | 2015-04-01 | D | Yes, this is a new mapping layer that has not yet been announced.
There is an entry for O & G Pipeline Rights of Way under the O & G section but there is also a Crown Rights of Way under the Crown Tenure section. The 1st has ‘no overlap’ the 2nd shows that there is a O & G pipeline with overlap. Would these not be the same? | Chris K | 2015-04-01 | D | These are different data souces. WHSE_TANTALIS.TA_CROWN_RIGHTS_OF_WAY_SVW vs WHSE_MINERAL_TENURE.OG_PIPELINE_RW_PUB_SP
If there will always be a BCGS map number then NTS Grid is not very useful. If there are cases where there is no BCGS map number then NTS would be more useful. Are you able to break the NTS grid down to the next level? For example, 92G-15. | Chris K | 2015-04-01 | D | Decided that both of these layers are useful for other analysis
Recreational Trails – data provides length of overlap but doesn’t indicate what trail or trail system is called. Is there a name field? | Chris K | 2015-04-01 | Y | Added PROJECT_NAME and FOREST_FILE_ID fields
Format of spreadsheet – I would ‘top align’ or ‘centre align’ the rows is easier to read when you have lots of data | Chris K | 2015-04-01 | Y | Center Aligned
Create a summary of the Mineral/Coal Data to be added to the email. | Karen S | 2014-04-01 |  | Manually entering summary into email. Possibly create summary through python.
Regional Parks. Coal team really interested in this. As per Chris K's comment. Find out how current this data is. Who created it? | Tim M | 2017-04-01 | Y | The data is current. It is regional parks as designed by municipalities and provicial regional districts. Changed the name to better reflect the layer
Add HEWR, LEWR + kernel data to report | Tim M | 2017-04-01 | Y | Herd information was already in the report. Added kernel information. Spoke to Tim M and decided that onlyt a total area per kernel distribution is required. Added dissolve to the script to get a total of each distribution.gernal
Environmental Assessment data points (Environmental Inspection Points?) | Tim M | 2017-04-01 | Y | Added WHSE_ENVIRONMENT_ASSESSMENT.EPIC_PROJECT_POINTS_SVW
Create pdf's from reports to circumvent printing issues. Can be used to send via email. | Tim M | 2017-04-01 |  | Look into com object library to crete an instance of a pdf from the excel table.
Add O&G Pipeline ROW field (LAND_TYPE) to indicate if it's 'Private', Crown' or 'Both' | Mike M | 2013-05-01 | Y
Update input feature class/shapefile to accommodate more tahn one feature for area of interest | Rob O/Mike M | 2002-07-01 |  | The area of interest shapefile or feature class may contain more than one feature. The tool can only accpet one at this point. Find a way around this. (merge, how to set field mappings?)
Have the input polygon area in hectares automatically listed under "Area Of Interest Information" | Rob O
1.9
1.8